|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Month of 2016** | **Activity** | **Organisation(s)** | **Output** | **STATUS** |
| Jan.-Mar. | Analysis of experiences with the use of Facebook to track, discuss and communicate hare hunting, Faroe Islands | Univ. Faroe Islands | Manuscript for journal paper | Draft converted into a section in chapter in CUP book. Published June 2017 |
| Mar. onwards | Continued pilot testing of templates Jukajoki and Näätämo watersheds, Finland | SnowChange | Technical report | Report received and circulated |
| Mar. | Pilot testing of templates begin in Finnmarken, Norway | ICRH | Technical report | Deadline 13/6 2017 |
| Mar. | Inter-active meeting in the Technical Backing Group for the project | Members of the Technical Backing Group | Minutes | Meeting held in Dec 2016. Minutes in prep. |
| May-August | Continued pilot testing of templates Arsuk, Isortoq, and Nanortalik, Greenland | APNN, GINR, NORDECO | Technical report | Short report prepared |
| To be determined | Preparation of policy brief(s) for Nordic Council of Ministers | All | Policy Brief | Policy brief discussed with NCM Secretariat; graphic contents drafted |
| To be determined | Training course | To be determined | One-page intro manual drafted by participants | Not yet |
| To be determined | International workshop | All | Workshop report | Workshop on Nunavis held in Nuuk Dec 2016, external minutes have been drafted |
| Nov. or Dec. 2016 | Second Steering Committee Meeting | Members of the Project Steering Committee | Minutes | Postponed to June 2017 |
| Dec. 2016 | Progress report 2016 | APNN and NORDECO | Status Report | To be drafted in advance of the 22 June meeting |